DOCUMENT NAME

| document APPROVAL |  |  |
| --- | --- | --- |
| EntITY | DATE OF BOARD MEETING | BOARD RESOLUTION NUMBER |
| BOARD OF DIRECTORS |  |  |
| ENTITY | DATE OF EXCO MEETING | MINUTE NUMBER |
| EXECUTIVE COMMITTEE |  |  |

| SIGN OFF AND REVISION RECORD |  |  |  |  |
| --- | --- | --- | --- | --- |
| Rev | Description | Originator | Reviewer | Date |
| A | Original Issue |  |  |  |

Table of Contents

1	1. Context & Objectives (RFP Alignment)	1

2	2. Detailed Methodology (ECSA Stages 1–4)	1

2.1	Stage 1 — Inception (Weeks 1–4)	1

2.2	Stage 2a — Concept & Viability / Preliminary Design (Weeks 5–14)	1

2.3	Stage 2b — Detailed Assessments & Statutory Approvals (Weeks 15–26)	1

2.4	Stage 3* — Detailed Design (Weeks 27–34)	1

2.5	Stage 4* — Documentation & Procurement (Weeks 35–40)	1

3	3. Preliminary Project Plan (Milestones & Durations)	1

4	4. Project Management: Approach & Methodology	1

4.1	Governance & Roles	1

4.2	Planning, Controls & Reporting	1

5	5. Risk Management (ISO 31000:2018)	1

6	6. Quality Assurance & Control (ISO 9001:2015)	1

7	7. Additional Services (per ECSA Guidelines & RFP Pricing Instructions)	1

8	8. Deliverables Register (Mapped to RFP Tables 1–2)	1

9	9. Assumptions & Dependencies	1

# 1. Context & Objectives (RFP Alignment)

Overstrand Municipality manages approximately 860 km of bulk and reticulation water pipelines—predominantly asbestos cement at end-of-life—and several areas remain dependent on septic/conservancy tanks. This assignment prepares two priority projects to bankability and procurement readiness, aligned to ECSA Stages 1–4 and the IFC Performance Standards / World Bank ESS.

Project A – Water Reticulation Pipeline Replacement: HDPE renewal and selective upsizing in Kleinmond, Betty’s Bay, Pringle Bay, Rooi‑Els and Hermanus; trenchless methods where feasible.

Project B – Sewer Network Extension: Extensions in Hermanus, Hawston and Fisherhaven; likely new pump stations; transition away from tanker operations.

Outputs, meeting cadence and the Stage‑2 feasibility gate are mapped to the RFP’s Tables 1–2 (deliverables), Table 3 (meetings) and Section 3 (procurement approach).

# 2. Detailed Methodology (ECSA Stages 1–4)

Progression to Stages 3–4 is contingent on feasibility confirmation at the end of Stage 2. Stages 1–2b are fixed-fee; Stages 3–4 are re‑priced against the confirmed cost of works per the RFP’s procurement approach.

## Stage 1 — Inception (Weeks 1–4)

Kick‑off; data‑room; collect Master Plans (Water/Sewer), WSDP/IDP inputs, pipe burst data, Minimum Standards, and prior studies.

Site reconnaissance for tie‑ins and constructability; identify candidate trenchless sections (A) and pump‑station sites (B).

Demand–supply validation (incl. seasonal peaks); status‑quo diagnostics; prioritisation logic linked to failure records (A) and septic‑to‑sewer catchments (B).

Preliminary ESIA screening (IFC/ESS lens) and approvals pathway (Basic Assessment vs EIA; potential WUL).

Institutional & regulatory assessment; stakeholder mapping; initial risk register and mitigation concepts.

Deliverable: Inception Report with Options Analysis & Preliminary ESIA.

## Stage 2a — Concept & Viability / Preliminary Design (Weeks 5–14)

Project A: Hydraulic modelling; HDPE class selection; PRVs and bulk metering; trenchless feasibility (HDD, pipe bursting); upstream pumps/reservoir adequacy checks.

Project B: Hydraulic concept for gravity/rising mains; pre‑sizing of pump stations (N+1 duty/standby); odour/noise control and energy‑efficiency; WWTW capacity checks.

Shared: Lifecycle costing (CAPEX/OPEX/renewal), affordability and maximum viable debt; revenue enhancement (tariffs, development charges, smart metering/billing).

Shared: ESIA scoping & ESMP outline; climate‑resilience features; Implementation & Procurement Plan; Impact Statement (A: NRW % and ML/d; B: indigent households & GHG reduction).

## Stage 2b — Detailed Assessments & Statutory Approvals (Weeks 15–26)

Environmental baseline and Basic Assessment/EIA (as triggered) with public participation; permitting (incl. WUL where applicable).

Geotechnical investigations; cadastral/topographic surveys; servitudes/wayleaves; land access agreements.

Update risk register, cost estimates and constructability plan; confirm traffic/access and reinstatement strategies.

Deliverables: Specialist reports and statutory approvals; updated estimates and risk register.

## Stage 3* — Detailed Design (Weeks 27–34)

Construction‑ready designs aligned to Overstrand Minimum Standards; appurtenances (PRVs, air valves, meters); trenchless sections; SCADA interfaces.

Project B: Pump‑station mechanical/electrical design; wet‑well sizing; controls; odour and noise mitigation.

BoQs and ±10% cost estimate; authority submissions; Employer’s Requirements and specifications. (Subject to Stage‑2 gate.)

## Stage 4* — Documentation & Procurement (Weeks 35–40)

Complete tender packs (conditions, specs, drawings, pricing schedules, ESMP clauses, skills development requirements).

Tender briefing & queries; addenda; evaluation framework; evaluation & recommendation; priced contract documentation.

# 3. Preliminary Project Plan (Milestones & Durations)

| ECSA Phase | Weeks | Key Milestones / Outputs (Projects A & B) |
| --- | --- | --- |
| Stage 1 – Inception | 1–4 | Kick‑off; data/site review; Inception Report with Options Analysis & Preliminary ESIA; stakeholder map; initial risk register |
| Stage 2a – Concept & Viability | 5–14 | Preliminary designs & modelling; Feasibility & Financial Model; Implementation & Procurement Plan; Impact Statement |
| Stage 2b – Assessments | 15–26 | Environmental baseline & BA/EIA; Geotech; Land/Topo; permits; updated estimates and risk register |
| Gate – Feasibility decision | 26 | PMU decision; confirm Stage 3–4 scope and fees per procurement approach |
| Stage 3* – Detailed Design | 27–34 | Final drawings/specs; BoQs; authority submissions; ±10% estimate |
| Stage 4* – Docs & Procurement | 35–40 | Tender packs; briefing & queries; evaluation framework & recommendation |

Meeting cadence: monthly progress (GreenCape–PSP), quarterly PSC, ~8 municipal authority meetings, and ad‑hoc engagements with DWS/DFFE.

# 4. Project Management: Approach & Methodology

## Governance & Roles

Project Director (PrEng/PrTech Eng) – accountability, client interface, stage‑gate approvals.

Project Manager – delivery management, schedule/cost/quality control, risk & change management.

Discipline Leads – Civil/Design, Project Finance/Economics, Environmental & Social/Permitting, Legal/Contracts.

RACI – decision rights defined per workstream.

## Planning, Controls & Reporting

Integrated master schedule with 2‑weekly look‑aheads; critical‑path management; approvals/servitudes/survey dependencies tracked.

Scope baseline anchored to RFP Tables 1–2; formal change control with impact assessment.

Cost control and earned value; independent estimate challenge at Stage 3; Stage 3–4 fee re‑pricing after Stage 2 gate.

Information management: controlled document register; drawing/version control; decision/risk/action logs; transmittals.

Stakeholder engagement: plan and log aligned to IFC/ESS; grievance mechanism; scheduled disclosures.

Reporting: monthly progress packs; quarterly PSC decks; risk/issue dashboards; E&S compliance tracker.

# 5. Risk Management (ISO 31000:2018)

A risk framework and process consistent with ISO 31000:2018 is integrated with design and E&S work; a living risk register is maintained and reviewed monthly and at stage gates.

Establish context (strategic, regulatory, E&S, technical, financial).

Identify risks (permitting BA/EIA/WUL, ground/heritage constraints, constructability, affordability, supply chain, community acceptance, O&M capacity).

Analyse (probability–impact; bow‑tie/fault‑tree for top threats; quantify schedule/cost exposure).

Evaluate (prioritise against criteria and appetite; define triggers and early‑warning indicators).

Treat (avoid/reduce/transfer/accept with monitoring; assign owners, budgets and due dates; integrate into schedule & design).

Monitor & review (monthly reviews; PSC escalations; trigger‑based re‑assessment after material findings).

Communicate & consult (aligned to stakeholder plan and IFC/ESS engagement expectations).

# 6. Quality Assurance & Control (ISO 9001:2015)

A process‑based QMS (Plan–Do–Check–Act) underpins delivery, applying risk‑based thinking and continual improvement.

Quality planning per stage – acceptance criteria mapped to RFP deliverables (e.g., Stage 2 Feasibility; Stage 3 drawings/BoQs to ±10%; Stage 4 tender completeness).

Design & development controls – design basis; calcs/models; interdisciplinary reviews; independent peer review and formal design verification; validation to Overstrand Minimum Standards.

Document control – master register; versioning; transmittals; audit trail; records retention and retrieval.

Control of external providers – competence & QA for environmental baseline, geotech and surveys; acceptance of third‑party outputs.

Nonconformity & corrective action – issue logging, root‑cause analysis, corrective actions and effectiveness checks.

Internal audits & management review – periodic audits; management review of risks/opportunities, KPIs and client feedback.

Competence & training – ECSA‑registered professionals as appropriate; targeted skills transfer to municipal staff.

# 7. Additional Services (per ECSA Guidelines & RFP Pricing Instructions)

Additional Services beyond Normal Services will be scoped and priced per the ECSA Guideline. Specialist services (e.g., surveys, testing, investigations) are reimbursable on actual cost plus an administration fee, subject to GreenCape pre‑approval and competitive procurement.

Specialist surveys & investigations: environmental baseline, geotechnical, topographic/cadastral; servitude/wayleave support.

NRW diagnostics & pressure management (Project A): DMA definition, acoustic leak detection, meter audit/specification, pressure optimisation.

Advanced modelling & analytics: transient analysis (water); I/I assessment and inflow control (sewer); pump energy modelling.

Climate resilience & energy optimisation: flood/heat risk integration; energy audits for pump stations; GHG accounting for Impact Statement.

Procurement packaging advisory: lotting strategy, market sounding, risk allocation and form‑of‑contract alignment.

Stakeholder facilitation: enhanced SEP and grievance mechanism aligned to IFC/ESS; local SMME participation planning.

O&M transition & training: SOPs, spares lists, commissioning and handover packs; skills uplift.

Independent Cost Estimate (ICE): third‑party challenge of Stage 3 BoQs and rates.

# 8. Deliverables Register (Mapped to RFP Tables 1–2)

| Stage | Key Deliverables |
| --- | --- |
| Stage 1 | Inception Report; Options Analysis; Preliminary ESIA; Stakeholder map; Risk register; Institutional/regulatory assessment. |
| Stage 2a | Concept designs; Feasibility & Financial Model; ESIA scoping & ESMP outline; Implementation & Procurement Plan; Impact Statement (A: NRW % & ML/d; B: households & GHG). |
| Stage 2b | Specialist assessments and statutory approvals (environmental baseline/BA/EIA; geotech; land/topo); updated estimates; updated risk register. |
| Stage 3* | Detailed Design Report; drawings/specs; BoQs; authority submissions; ±10% estimate. |
| Stage 4* | Complete tender documentation; evaluation framework & recommendation; priced contract documentation. |

# 9. Assumptions & Dependencies

Timely access to Master Plans, burst data, standards and wayleave processes; availability of municipal stakeholders per RFP meeting schedule.

Statutory processes (BA/EIA, WUL) proceed within typical durations; extended timeframes reflected in Stage 2b schedule.

Stage 3–4 execution and fee update contingent on the Stage 2 feasibility gate per the RFP procurement approach.